## elr-project-process-t
Project Process Template
Real Estate
Name | Owner | Status | Estimated Days | How long will this take - Start | How long will this take - End | Date | Files
Business Case
Signed Lease
LOD (PDF & AutoCAD files)
Affection Plan
Building Completion Certificate
DCD approved drawings
DM approved drawings
Ejari /Tawfeeq
Trade License
0
Design
Name | Owner | Status | Estimated Days | How long will this take - Start | How long will this take - End | Date | Files
Site Survey with PM & Designer |  |  | 3
Concept Layout & Sketch |  |  | 7
Ops Signature |  |  | 7
Schematics (LL) |  |  | 7
LL DD1 |  |  | 7
LL DD2 |  |  | 14
LL DD3
Kitchen Design
45
Tender process
Name | Owner | Status | Estimated Days | How long will this take - Start | How long will this take - End | Date | Files
Create ( BOQ) |  |  | 7
Issue Tender |  |  | 14
Tender Analysis |  |  | 4
Tender Approval |  |  | 4
Issue (LOA) |  |  | 4
Issue (LPO) |  |  | 4
37
Site works
Name | Owner | Status | Estimated Days | How long will this take - Start | How long will this take - End | Date | Files
ELR issue NOC to GC for Authority
Kick off meeting with LL and Contractor |  |  | 1
First site visit (first Fix) |  |  | 15
Second Site Visit (Second Fix) |  |  | 15
Authority Inspection (DEWA/DCD/DM/FC/DC) |  |  | 10
Kitchen equipment delivery |  |  | 5
IT installation on site. ( Micros/ PC) |  |  | 5
Furniture Delivery |  |  | 2
First Snagging with Contractor prior to handover |  |  | 7
60
Site Handover
Name | Owner | Status | Estimated Days | How long will this take - Start | How long will this take - End | Date | Files
PM arranges first Handover meeting with Ops/Designer & Contractor |  |  | 1
List of Snagging issued to Contractors |  |  | 2
PM arranges final Handover to Ops Team. |  |  | 1
Store opens |  |  | 1
Final snagging or extras given to Contractors |  |  | 7
12
Procurement
Name | Owner | Status | Estimated Days | How long will this take - Start | How long will this take - End | Date | Files
Quantity Surveyor (BOQ)
Kitchen equipment
Kitchen Counter Display units
Stainless Steel Counter
Lighting Fixtures
Du/Etisalat Connection
Digital Screens
Delivery of Coffee Machines
Delivery Of Coffee Grinders
Micros Till Setup
BOH PC setup
Coffee Machine Calibration
Floorworks
Grease traps
Plants
Furniture
Signage,Artworks,Acrylics
Offices Chairs
Safety Vault
Coffee Cup Dispensers*
Knock out Drawers*
0